HCMUT DETAILED PLAN PROPOSAL

AI Model Training for AD L4 Robotaxi Systems

Quantitative Deliverables & Measurable Acceptance Criteria

Client: VinFast - L4 Team

Provider: Ho Chi Minh City University of Technology (HCMUT)

Project Duration: 10 months (September 1, 2026 - June 30, 2027)

Version: 1.0 - Detailed Specification

This proposal provides concrete, measurable deliverables and acceptance criteria for all project milestones to ensure transparent evaluation and successful deployment.

# PROJECT OVERVIEW

In order to foster effective collaboration and promote technological advancement in the development of Level 4 (L4) Autonomous Driving (AD) systems, Ho Chi Minh City University of Technology (HCMUT), in partnership with VinFast’s L4 Team, will undertake a research and development project focused on developing a World Model architecture for autonomous driving systems.

This project aims to transition from computationally intensive 3D external simulators toward an evaluator-free latent closed-loop simulation framework, optimized for dense and complex traffic environments in Vietnam, particularly those characterized by a high density of motorcycles.

## Project Structure

The project is structured into three main phases:

- Phase 1 (3 months): Development of CaMo-JEPA for Self-Supervised Perception and Confounder Estimation.

- Phase 2 (4 months): Action-Conditioned Latent SCM Predictor & Anytime-Valid Causal Planner

- Phase 3 (3 months): Evaluator-Free Closed-Loop Evaluation, Fine-Tuning & Deployment

The project commences at HCMUT on September 1st, 2026, with periodic deliverables provided to VinFast at each milestone to ensure alignment and continuous progress towards system integration and deployment.

## Key Differentiator: Quantitative & Measurable Deliverables

This proposal differs from typical proposals by providing:

- Specific performance metrics with numerical thresholds (e.g., GPU FLOPs reduction ≥ 60%, Latent Drift ≈ 0)

- Concrete output formats (Latent Vectors, trajectories, MP4 rollout videos)

- Quantified test coverage (minimum driving hours, minimum rollout trajectories, minimum e-testing trials, dense scenarios)

- Objective acceptance criteria aligned with Sequential e-Testing (minimum driving hours, minimum rollout trajectories, minimum e-testing trials)

- Measurable resource-efficiency KPIs, since GPU cost reduction is a first-class deliverable of this architecture, not a side effect

This ensures transparent evaluation, clear acceptance gates, and successful deployment.

# PHASE 1: CAMO-JEPA PERCEPTION (3 MONTHS)

## Team Composition

To effectively deliver the objectives in Phase 1, the HCMUT team will consist of:

Phase 1 staffing and cost

| Role | Headcount | Monthly Cost (VNĐ) | Total (3 months) (VNĐ) |
| --- | --- | --- | --- |
| Project Leader | 1 | 13,500,000 | 40,500,000 |
| Teaching Assistant | 2 | 12,000,000 | 72,000,000 |
| Student | 5 | 6,000,000 | 90,000,000 |
| Total | 8 |  | 202,500,000 |

Responsibilities:

- Project Leader: Overall coordination, architecture design, causal-inference guidance, reporting

- Teaching Assistants: Data pipeline engineering, model training, factorization/confounder evaluation, documentation

- Students: Data collection support, experiments, evaluation

## Milestone 1: Proposed CaMo-JEPA Perception & Confounder Pipeline

Deadline: November 30th, 2026

### Input Data

- Multi-sensor data from VinFast VF8 sensor suite:

  - 8 multi-view cameras (RGB)

  - 12 LiDAR sensors

  - Radar, IMU, GNSS data

- VinFast proprietary dataset: Minimum 100 hours of continuous driving data collected on dense residential and mixed-traffic routes, including narrow streets, motorcycle-heavy intersections, and market streets. The dataset is expected to comprise 70% training data and 30% test data, with coverage targets of 50% clear daytime traffic conditions, 25% adverse weather conditions, and 25% high-traffic-density scenarios.

### Quantitative Performance Metrics

World Model performance requirements

| Metric | Target | Evaluation Method |
| --- | --- | --- |
| Old Knowledge Retention | Lrecon ≈ 0 | Cosine similarity (Lrecon=1-cos(zt, estatic)) against original ViT |
| Static-scene mIoU retention (lane, divider, sky) vs. original ViT baseline | ≥ 95% mIoU of original | Linear-probe segmentation head, frozen backbone |
| Near-body motorcycle detection (Linear Probe), mAccuracy, Flow branch ON | mAccuracy ≥ 80% | 500+ manually spot-checked near-body motorcycle events |
| Near-body motorcycle detection improvement, Flow ON vs. Flow OFF (IoU) | ≥ +15 pts of IoU | Flow ON vs. Flow OFF ablation |
| Latent Orthogonality | Lorth≈ 0 | Measure Difference Loss Lorth=zTtask . zexo2F |
| Mutual Information, I(zexo;at) | I(zexo;at) ≤ 0.05 nats | InfoNCE/MINE estimator, 3 independent runs: Prove independence of exogenous variables from ego-action |
| GPU backprop cost reduction vs. full ViT fine-tuning | Reduce by 70% | TFLOPs measured during training |

### Inference Performance Requirements

Perception backbone inference requirements

| Component | Platform | Max Latency |
| --- | --- | --- |
| Frozen ViT (16×16) encoder, 8 cams | RTX 4090 | ≤ 60ms (batched) |
| FlowFormer++ flow branch, 8 cams | RTX 4090 | ≤ 30ms (batched) |
| Fusion + Causal Factorization | RTX 4090 | ≤ 10ms |
| Total perception latency | RTX 4090 | ≤ 100ms |
| Total perception latency | Jetson AGX Orin | ≤ 250ms |
| Minimum FPS |  | ≥ 10 FPS |

### Model Interface (Internal Phase 1 to Phase 2 Data Flow)

All outputs must be in standardized, machine-readable formats:

- Latent Tensors:

  - Format: PyTorch Tensor (torch.Tensor) zt∈ ℝ(N×D), decomposed and saved separately as ztask,t, zexo,t

  - Sampling: Temporally aligned to the sliding window FrameBatch clips (default T = 16 frames, stride = 1)

- Confounder Vector:

  - PyTorch Tensor (torch.Tensor) Ut∈ ℝ(DU) with DU = 128, from GRU Confounder Encoder.

  - Exported per-batch as the final hidden state summarizing the (T-1) temporal history window: Ut=hT-1=GRU(SpatialMeanPool(zfused))

### Robustness Requirements

Robustness validation requirements

| Condition | Min Test Frames | Latent-Drift Target |
| --- | --- | --- |
| Clear weather (baseline) | 500 | ≤ 0.05 (reference) |
| Light rain | 500 | ≤ 0.07 |
| Heavy rain | 500 | ≤ 0.08 |
| Fog | 500 | ≤ 0.10 |
| Night (low light) | 500 | ≤ 0.10 |
| TOTAL | 2,500+ frames |  |

Maximum accuracy drop: ≤ 15% relative increase in Latent Drift across all adverse conditions vs. clear-daylight baseline

### Phase 1 Deliverables (Specific Formats)

- Diagnostic Visualization:

  - Optical-flow heatmap overlay video (MP4) highlighting near-body motorcycle motion, minimum 5 demo clips, 30–60s each

  - Cosine-similarity drift plot per driving segment (PNG/CSV)

- Model Checkpoints:

  - PyTorch:

    - camo.pt: The most recent checkpoint (Overwrite at the end of each epoch).

    - best_camo.pt: The checkpoint with the best (lowest) Average Loss to date.

    - step_{batch_idx}.pt: Mid-epoch checkpoint saved after a certain number of steps.

  - State Dict: Strictly contains trainable modules only (flow_encoder, fusion, factorizer, confounder, predictor) to minimize file size; frozen backbones are excluded.

  - ONNX export (optional): camo.onnx

- Training Scripts:

  - Reproducible training: fixed random seed, config YAML/CaMoJEPAConfig with all hyperparameters (freeze flags, loss weights, ablation flags, ViT & FlowFormer++ paths)

  - Training logs: TensorBoard format, ≥ 50 epochs

  - Result variance: ≤ 2% across 3 independent runs

- Evaluation Scripts:

  - Cosine-similarity / Latent-Drift calculator (CLI, JSON/CSV output)

  - Orthogonality-loss and Mutual-Information (or action-leakage proxy) estimator scripts

  - Ablation harness: motion branch off, confounder off (U=0), factorizer off

  - Linear-probe evaluation harness for near-body / small-motion (e.g. motorcycle), comparing static-only vs. static+motion

  - Resource script: GPU memory and time/step under frozen ViT + frozen FlowFormer++

- Unit Tests:

  - Test coverage: ≥ 80% for causal modules, fusion, losses, and phase1 wiring

  - Framework: pytest or unittest

  - Automated CI: GitHub Actions or equivalent

### Dataset Requirements

Perception-phase data coverage

| Source | Volume | Purpose |
| --- | --- | --- |
| VinFast 8-cam footage (current) | 20 minutes | Initial validation, sanity checks |
| VinFast new 8-cam collection | ≥ 100 hours | Including both training and test sets, sufficient for statistically meaningful probing and MI estimation |
| Legacy NAVSIM dataset | Reused, existing set | Auxiliary comparison only (not required for training) |
| Total new raw video | ≥ 100 hours + legacy | Comprehensive validation |

# PHASE 2: ACTION-CONDITIONED PREDICTION & CAUSAL PLANNING (4 MONTHS)

## Team Composition

For Phase 2, HCMUT will expand the team to cover predictive modeling and reinforcement-learning planning workloads:

Phase 2 staffing and cost

| Role | Headcount | Monthly Cost (VNĐ) | Total (4 months) (VNĐ) |
| --- | --- | --- | --- |
| Project Leader | 1 | 13,500,000 | 54,000,000 |
| Teaching Assistant | 3 | 12,000,000 | 144,000,000 |
| Student | 5 | 6,000,000 | 120,000,000 |
| Total | 9 |  | 318,000,000 |

Deadline: March 31st, 2027

## Milestone 2.1: Action-Conditioned Latent SCM Predictor

### Input Data

- ztask,t, zexo,t, Ut sequences from Milestone 1 output, aligned with ego-action log at (steering, throttle/brake)

- Multi-sensor data from VinFast VF8 sensor suite:

  - 8 multi-view cameras (RGB)

  - 12 LiDAR sensors

  - Radar, IMU, GNSS data

- VinFast proprietary dataset: Minimum 100 hours of continuous driving data collected on dense residential and mixed-traffic routes, including narrow streets, motorcycle-heavy intersections, and market streets. The dataset is expected to comprise 70% training data and 30% test data, with coverage targets of 50% clear daytime traffic conditions, 25% adverse weather conditions, and 25% high-traffic-density scenarios.

### Quantitative Performance Metrics

Latent SCM predictor performance requirements

| Metric |  |  | Target |
| --- | --- | --- | --- |
| 1-step latent prediction error (L2, normalized) |  |  | ≤ 0.08 |
| Causal Dynamics Loss (vs. ground-truth z_t+1) |  |  | ≤ 0.10 |
| 3-second rollout ADE (decoded ego-trajectory) |  |  | ≤ 1.0m |
| 3-second rollout FDE (decoded ego-trajectory) |  |  | ≤ 2.0m |
| do(a_t) intervention consistency: I(z_exo ; a_t) post-predictor |  |  | ≤ 0.05 nats |
| Redundant rollout-compute reduction (z_exo computed once for 32 branches) |  |  | 30% – 40% |

### Inference Performance

- Predictor latency (1 step, RTX 4090): ≤ 5ms per branch, batched across 32 branches ≤ 30ms total

- Predictor latency (Jetson AGX Orin, 1 step): ≤  15ms per branch, batched across 32 branches ≤ 60ms total

### Phase 2.1 Deliverables

- Pre-trained Models:

  - PyTorch checkpoint: scm_predictor_task.pth, scm_predictor_exo.pth

  - ONNX export

- Training Artifacts:

  - Training logs: TensorBoard with ≥ 30 epochs

  - Config files: YAML with all hyperparameters documented

  - Checkpoints: Best and last epoch models

- Evaluation Scripts:

  - ADE/FDE calculator

  - Causal Dynamics Loss logger

  - JSON metric export

- Visualization:

  - Minimum 5 examples of predicted-vs-ground-truth latent-decoded trajectory overlays

## Milestone 2.2: Anytime-Valid Causal Planner (Latent RL Planner)

### Input Data

- ztask,t, zexo,t, Ut sequences from Milestone 1 output, aligned with ego-action log at (steering, throttle/brake)

- Multi-sensor data from VinFast VF8 sensor suite:

  - 8 multi-view cameras (RGB)

  - 12 LiDAR sensors

  - Radar, IMU, GNSS data

- VinFast proprietary dataset: Minimum 100 hours of continuous driving data collected on dense residential and mixed-traffic routes, including narrow streets, motorcycle-heavy intersections, and market streets. The dataset is expected to comprise 70% training data and 30% test data, with coverage targets of 50% clear daytime traffic conditions, 25% adverse weather conditions, and 25% high-traffic-density scenarios.

### Planning & Safety Performance

Anytime-valid planner requirements

| Metric | Target |
| --- | --- |
| Rollout trajectory candidates per planning cycle | 32 |
| Rollout Collision Rate (simulated, latent space) | ≤ 5% |
| Off-road / lane-violation rate (simulated) | ≤ 5% |
| Planning latency per cycle (32 branches, RTX 4090) | ≤ 80ms |
| Anytime-Valid Early-Stopping (Ville’s Inequality), reduction in rollout steps vs. fixed-horizon rollout | 50%– 70% |
| False early-stop rate (safe trajectory wrongly cut) | ≤ 5% |
| Threshold: e-process Eτ ≥ 1/α, with α | 0.05 |

### Output Format Specifications

- Trajectory Output:

–	Format: JSON, minimum 8 waypoints per trajectory, sampling interval 0.5s

–	Schema: {"trajectory": [{"t":..,"x":..,"y":..,"heading":..,"v":..}], "risk_score": 0.0-1.0, "branch_id": ...}

–	Coordinates in vehicle reference frame

- Rollout Video:

–	Format: MP4, one clip per demo scenario, 1–2 minutes each, minimum 10 demo clips

–	Content: side-by-side predicted latent-decoded rollout vs. ground-truth future frames, with overlaid planned trajectory and risk score

- Confidence/Risk Score: e-value per trajectory branch, range [0, 1/α], logged per rollout

### Phase 2.2 Deliverables

1.	Planner Components: RL Policy Agent checkpoint, e-process early-stopping module, cost-function weights (YAML, ≤ 15 tunable parameters)

2.	Baseline Comparison Scripts: automated comparison vs. Drive-JEPA + NAVSIM closed-loop baseline on the reused legacy labeled set

3.	Docker Container: reproducible environment, tested on clean machine

### Dataset Requirements

• 	Cumulative training data: ≥ 100 hours (8-cam + CAN Bus)

•	Legacy labeled (“NAVSIM-style”) set: reused for baseline comparison scenarios, minimum 30 routes

### Documentation

- Technical report: minimum 20 pages

- Model architecture: planner architecture (SCM Predictor + RL Policy + Early-Stopping), pseudocode for Ville’s-inequality stopping rule

- Evaluation results: tables, precision-recall curves, confusion matrices

- API documentation: all functions documented

- Comparison study: vs. minimum 2 baseline methods

# PHASE 3: EVALUATOR-FREE CLOSED-LOOP EVALUATION, FINE-TUNING & DEPLOYMENT (3 MONTHS)

## Team Composition

To effectively deliver the objectives in Phase 3, the HCMUT team will consist of:

Phase 3 staffing and cost

| Role | Headcount | Monthly Cost (VNĐ) | Total (3 months) (VNĐ) |
| --- | --- | --- | --- |
| Project Leader | 1 | 13,500,000 | 40,500,000 |
| Teaching Assistant | 2 | 12,000,000 | 72,000,000 |
| Student | 5 | 6,000,000 | 90,000,000 |
| Total | 8 |  | 202,500,000 |

Responsibilities:

- Project Leader: Overall coordination, architecture design, causal-inference guidance, reporting

- Teaching Assistants: Data pipeline engineering, model training, factorization/confounder evaluation, documentation

- Students: Data collection support, experiments, evaluation

## Milestone 3: Latent Closed-Loop Simulation & Sequential e-Testing

Deadline: May 31st, 2027

### Input Data

- Full CaMo-JEPA pipeline and output from phase 2

- Multi-sensor data from VinFast VF8 sensor suite:

  - 8 multi-view cameras (RGB)

  - 12 LiDAR sensors

  - Radar, IMU, GNSS data

- VinFast proprietary dataset: Minimum 100 hours of continuous driving data collected on dense residential and mixed-traffic routes, including narrow streets, motorcycle-heavy intersections, and market streets. The dataset is expected to comprise 70% training data and 30% test data, with coverage targets of 50% clear daytime traffic conditions, 25% adverse weather conditions, and 25% high-traffic-density scenarios.

### Closed-Loop Evaluation Metrics

Evaluator-free closed-loop requirements

| Metric | Target |
| --- | --- |
| Correlation of internal Latent Closed-Loop score vs. external NAVSIM/CARLA-based score (Pearson r) | ≥ 0.85 |
| Sequential e-Testing time reduction vs. fixed-sample testing | 40% – 60% |
| Type-I error (false-pass rate) under sequential testing | ≤ α = 0.05 |
| Total GPU FLOPs reduction, full pipeline vs. Drive-JEPA + external simulator baseline | 60% – 80% |

### Mandatory Demo Scenarios (Vietnamese Dense-Traffic Specific)

Mandatory demo scenarios

| No. | Scenario Name | Description |
| --- | --- | --- |
| 1 | Motorcycle side-cut avoidance | Motorcycle cutting in from blind spot at low speed |
| 2 | Dense market-street weaving | Narrow street, > 15 motorcycles in frame |
| 3 | Residential alley merge | Narrow alley merging into main road, no lane markings |
| 4 | Mixed-traffic intersection | 4-way, no traffic light, negotiated right-of-way |
| 5 | Pedestrian + motorcycle mix | School-zone-like crossing with mixed traffic |
| 6 | Rain + dense traffic | Reduced visibility, adverse weather |
| 7 | Night residential driving | Low light, unmarked lanes |
| 8 | Sudden stop (lead vehicle) | Hard-braking lead motorcycle/car |
| 9 | Parked-vehicle door/obstacle | Static obstacle avoidance, narrow clearance |
| 10 | Full route, mixed conditions | 10 – 15 min end-to-end residential + arterial route |

### Success Criteria

- 10/10 scenarios pass in Latent Closed-Loop Simulation

- 0 simulated collisions, 0 critical rule violations

- Trajectory + rollout video delivered for each of the 10 scenarios

### Documentation

- Technical report: minimum 20 pages

- Comparison study: correlation study methodology, e-testing derivation

## Milestone 4: Fine-Tuning, Optimization, KPI Validation & Deployment Package

Deadline: June 30th, 2027

### Optimization Targets (Measurable Improvements)

Model optimization requirements

| Optimization | Target | Measurement |
| --- | --- | --- |
| Inference speedup (TensorRT) | ≥ 2× | vs. PyTorch baseline |
| FP16 accuracy drop | ≤ 1% | vs. FP32 baseline |
| INT8 accuracy drop | ≤ 3% | vs. FP32 baseline |
| Model size reduction | ≥ 40% | Quantization + pruning |
| Memory footprint | ≤ 40GB | GPU RAM on Jetson AGX Orin |

### Final Resource-Efficiency Validation (Cumulative Contribution of the 3 Mathematical Tools)

Model optimization requirements

| Component | Mechanism | Target Savings | Measured |
| --- | --- | --- | --- |
| Frozen ViT + Zero-Init Fusion | Backprop only on FlowFormer++ branch | ≥ 70% backprop cost | (filled in at acceptance) |
| Causal Factorization (do-operator) | zexocomputed once for 32 branches | 30% – 40% rollout compute | (filled in at acceptance) |
| Anytime-Valid Rollout (Ville’s Inequality) | Early-exit high-risk branches | 50% – 70% rollout compute | (filled in at acceptance) |
| Sequential e-Testing | Real-time stopping on confidence | 40% – 60% test time | (filled in at acceptance) |

### Deployment Deliverables

- TensorRT Engines: camo_jepa_encoder.trt, scm_predictor.trt, latent_planner.trt

- Model Zoo (versioned, semantic versioning):

models/
 ├── perception/
 │   └── v1.0/{model.pth, model.onnx, model.trt, config.yaml}
 ├── scm_predictor/
 ├── latent_planner/
 └── closed_loop_eval/

- Inference Benchmarks: CSV — Model, Platform, Precision, Latency (ms), FPS, Memory (MB)

- Deployment Guide: step-by-step Jetson AGX Orin installation, minimum 10 pages, troubleshooting section

- Docker Image: ≤ 15GB, tested on clean Ubuntu 22.04, includes ROS 2 Humble + TensorRT + all dependencies

- End-to-End Scenario Package (per each of the 10 mandatory scenarios): trajectory JSON + rollout MP4 + risk-score log, delivered as a single archive

### Evaluation Process

- Automated Tests:

– CI/CD pipeline

– Unit tests ≥ 90% pass, integration tests 95% pass, linting checks pass

- Benchmark Evaluation:

– Evaluate on the legacy dataset using NAVSIM and labeled data

– Compare the results against Drive-JEPA baseline

– Generate automated report

- Latent Closed-Loop Simulation:

– Execute all 10 mandatory scenarios

– Log all metrics

– Generate success/failure report

### Documentation

- Technical report: minimum 30 pages

- Project coverage: all 3 phases and full system architecture

- Ablation study: key component and design analysis

- Resource validation: resource-savings evaluation

# DATA & HARDWARE REQUIREMENTS

## Data Requirements

### VinFast Must Provide

Data requirements from VinFast

| Data Type | Minimum | Notes |
| --- | --- | --- |
| Labeled frames (VF8) | 1,000 | Multi-sensor: cam + LiDAR + radar |
| New 8-camera multi-view raw video | ≥ 100h | Dense residential + mixed-traffic routes, ≥ 70% residential/market-street |
| CAN Bus / vehicle-state log | All sessions | Time-synced with video (steering, throttle/brake, speed, IMU) |
| HD maps | 5 routes | OpenDRIVE format |
| Ground truth annotations | All frames | KITTI or nuScenes format |

Delivery timeline: Week 1–2 of project start

Note on labeling: Because CaMo-JEPA is self-supervised, no new 3D bounding-box or HD-Map annotation is required for the new data — this is a deliberate design choice to reduce VinFast’s data-preparation burden versus the earlier Drive-JEPA/NAVSIM-based pipeline.

## Hardware Requirements

### Development (HCMUT Provides)

HCMUT development hardware

| Hardware | Specification |
| --- | --- |
| GPU workstation | 2× RTX 4090 or 4× RTX 3090 |
| CPU | AMD Ryzen 9 or Intel i9 |
| RAM | ≥ 64GB |
| Storage | ≥ 4TB SSD |
| Network | 10 Gbps Ethernet |

### Testing (VinFast Must Provide Access)

VinFast hardware access requirements

| Hardware | Requirement |
| --- | --- |
| NVIDIA Jetson AGX Orin | For deployment testing, remote access or on-site |
| VF8 vehicle | Min 40 hours access for validation phase |
| Proving ground | Min 10 days access for real-world testing |
| CARLA server | Remote access or cloud instance |
| Network storage | Min 2TB for dataset sharing |

Timeline:

- Week 1-2: Setup development environment

- Week 3-4: Data access and exploration

- Month 2-6: Continuous access for testing

- Month 8-10: Vehicle and proving ground access

# RISK MITIGATION PLAN

## Technical Risks

Risk assessment and mitigation

| Risk | Level | Mitigation Strategy |
| --- | --- | --- |
| New data volume arrives slower than 35h/month | High | Active-learning frame selection to maximize information from limited hours; transfer/pretrain flow branch on public driving video (e.g. BDD100K); heavy augmentation on the existing 20-min pilot for early iteration |
| Confounder/orthogonality not converging (MI leakage) | Medium | Adversarial MI minimization with hyperparameter search; fallback to simpler linear orthogonal projection; extended validation on synthetic confounder scenarios |
| SCM predictor drift over long rollout horizon | Medium/High | Shorter rollout horizon fallback (1.5s instead of 3s); ensemble predictors with uncertainty-aware early stop; conservative Ville’s-inequality tuning during early milestones |
| Latent Closed-Loop score does not correlate well with external simulator | Medium | Recalibrate against reused legacy labeled set; blend with limited external CARLA sanity-check if correlation target is not met |
| GPU resource shortage for 8-cam + 32-branch training | Medium | Cloud GPU burst rental (A100) budgeted as optional line item; reduce rollout branch count (32→16) as fallback |
| Vehicle/hardware testing access delayed | Low | Prioritize Latent Closed-Loop validation; treat real-vehicle spot-check as optional, post-milestone validation |
| Hardware unavailable | Low | Cloud GPU rental (AWS/Azure A100); simulation-only validation; budget for cloud: 100M VNĐ |
| Scope creep | Medium | Strict milestone gates; change-request process; weekly progress reviews |

## Contingency Plans

### If Milestone 1-2 Fails Acceptance

- Contingency buffer: +2 weeks for revision

- Alternative models: minimum 2 backup factorization/predictor variants prepared

- Minimum acceptable: 90% of KPI targets (instead of 100%)

- Additional support: Consult with external experts

### If VinFast Data Insufficient

- Fallback: Use public datasets exclusively

- Legacy labeled set: usable as-is for baseline comparison regardless of new-data volume

- Data collection: HCMUT can assist with 8-camera rig calibration and capture logistics

### If Hardware Access Delayed

## Quality Assurance

- Weekly Progress Reviews:

  - Every Friday, 1-hour meeting

  - Review metrics, address blockers

- Monthly Milestone Reviews:

  - Formal presentation to VinFast

  - Demo of current capabilities

  - Go/No-go decision for next phase

- Code Reviews:

  - All code reviewed by ≥ 2 team members

  - Pull request process

  - Automated CI checks

- Testing Protocol:

  - Unit tests: after each feature

  - Integration tests: weekly

  - End-to-end tests: bi-weekly

# COST SUMMARY

## Total Project Cost

Total project cost

| Phase | Cost (VNĐ) |
| --- | --- |
| Phase 1 – Perception Scale-Up (3 months) | 202,500,000 |
| Phase 2 – Prediction & Planning (4 months) | 318,000,000 |
| Phase 3 – Closed-Loop Eval & Deployment (3 months) | 202,500,000 |
| Total (Labor) | 723,000,000 |

## Payment Schedule

Payment schedule

| Payment | Milestone | Percentage | Condition |
| --- | --- | --- | --- |
| 1 | Contract signing | 30% | Advance payment, kick-off |
| 2 | Milestone 1 complete | 25% | Perception |
| 3 | Milestone 2 complete | 30% | Perception & Confounder Pipeline |
| 4 | Milestone 3-4 complete | 15% | Final optimization, handover |
|  | Total | 100% |  |

Payment amounts:

- Payment 1: 216,900,000 VNĐ (30%)

- Payment 2: 180,750,000 VNĐ (25%)

- Payment 3: 216,900,000 VNĐ (30%)

- Payment 4: 108,450,000 VNĐ (15%)

## Additional Costs (Optional)

Cloud GPU rental (if needed):

- 4× A100 GPUs for 3 months: 70,000,000 VNĐ

- Included in proposal contingency

Hardware (if VinFast needs to purchase):

- Workstation (i9 + RTX 4090): 100,000,000 VNĐ × 2 = 200,000,000 VNĐ

- Jetson AGX Orin: 30,000,000 VNĐ × 2 = 60,000,000 VNĐ

- Note: These are VinFast’s investment, not included in project cost

# PROJECT TIMELINE

Project timeline summary

| MS | Deliverable | Duration | Deadline (tentative) |
| --- | --- | --- | --- |
| 0 | Project kick-off | 1 week | Sep 1, 2026 |
| 1 | Perception Backbone at Scale | 3 months | Nov 30, 2026 |
| 2 | Latent SCM Predictor & Anytime-Valid Causal Planner | 4 months | March 31, 2027 |
| 3 | Closed-Loop Eval & e-Testing | 2 months | May 31st, 2027 |
| 4 | Fine-Tuning, KPI & Deployment | 1 months | June 30, 2027 |
|  | Total | 10 months |  |

## Gantt Chart (Simplified)

Project timeline (Gantt chart)

| Task | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Kick-off | X |  |  |  |  |  |  |  |  |  |
| Perception at Scale | X | X | X |  |  |  |  |  |  |  |
| Latent SCM Predictor & Causal Planner |  |  |  | X | X | X | X |  |  |  |
| Closed-Loop Eval |  |  |  |  |  |  |  | X | X |  |
| Fine-Tuning & Deploy |  |  |  |  |  |  |  |  | (X) | X |

## Value Proposition

HCMUT offers:

- A working CaMo-JEPA prototype already implemented at project start, reducing Phase-1 risk

- A fully self-supervised pipeline requiring no new 3D/HD-Map labeling, directly cutting VinFast’s data-preparation cost

- A causally-structured predictor that removes confounding bias present in naive behavior-cloning world models

- A simulator-free, labeling-free closed-loop evaluation methodology, reducing dependency on external NAVSIM/CARLA licensing and 3D annotation pipelines going forward

- Deep familiarity with Vietnamese urban/residential traffic patterns (motorcycle density, lane-less streets)

## Success Metrics

Project success will be measured by:

- Successful integration: Models run on VinFast hardware

- VinFast acceptance: All milestones accepted by VinFast team

- On-time delivery: All deadlines met

- On-budget: No cost overruns

- End-to-end deliverable completeness: trajectory JSON + rollout video delivered for all 10 mandatory scenarios

## Next Steps

- VinFast reviews this proposal (1 week)

- Clarification meeting (1 meeting, 2 hours)

- Contract negotiation (1 week)

- Contract signing (by August 30, 2026)

- Project kick-off (September 1, 2026)